## Status Report Template
SWE 3613 Status Report
IMPORTANT: File naming instructions
Name this file in the following manner: YYYYMMDD_TEAM_NAME_HERE.pdf
Example: 20120911_Group1.pdf
List Data - Do Not Edit
Project Name |  | Forager - Group 4 | [6 empty] | Completed | 1
Team Members |  | Robin Mays, Thomas Couture, Matthew Powell, Lee Hall | [6 empty] | Discarded | 2
Week Ending: |  | 2012-11-13 | [6 empty] | Development | 3
Cycle |  | Cycle 1 | [6 empty] | Testing | 4
System Metaphor |  | The system is designed to check through the entire SPSU domain and return a detailed report. This report should include all errors including dead links, missing images, scripts, and css files. All reports created should be stored and accessable through an easy to use user interface. These reports should also be sortable to make it easier to find certain reports, as well as comparable to each other to check and see the differences between them. It was also include features such as pausing, stoping, or restricting a search. | [6 empty] | Design | 5
Cycle Intent |  | The intent of this cycle is to get the added features of the product working. We plan to include sorting, printing, and comparing of the reports. We plan to be able to start a new scan of something previously scanned. Features to limit the scan based on certain criteria. Ability to pause and stop the scan. | [6 empty] | Unstarted | 6
ID | Use Case Name |  | Planned |  |  | Actual
|  |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
Crawler 1 | Basic Web Crawler |  | 2 | 20 | 5 | Development | 7 | 7
Crawler 2 | Record Crawler Results |  | 1 | 20 | 0 | Completed | 0 | 0
Report 1 | Show Scan Results |  | 2 | 30 | 4 | Development | 3 | 3
Report 2 | Crawler Interaction |  | 1 | 20 |  | Completed | 0
Report 3 | Sort Report |  | 2 | 10 | 10 | Unstarted | 8 | 8
Report 4 | Print Report |  | 2 | 10 | 10 | Unstarted | 0
Report 5 | Multiple Report Changes |  | 2 | 6 | 6 | Unstarted | 1 | 1
Report 6 | Live Report |  | 2 | 4 | 4 | Unstarted | 0
Crawler 3 | Runtime Limit |  | 2 | 12 | 12 | Unstarted | 0
Crawler 4 | Error Check |  | 2 | 10 | 10 | Unstarted | 5 | 5
SSL | Secure Check |  | 2 | 8 | 8 | Unstarted | 0
Report 7 | Subdomain Sort |  | 2 | 14 | 14 | Unstarted | 0
Login | User Login |  | 2 | 2 | 1 | Completed | 1 | 1
Crawler 5 | Pause Scan |  | 2 | 4 | 4 | Unstarted | 0
Crawler 6 | Timer |  | 2 | 6 | 2 | Unstarted | 0
Crawler 7 | Stopwatch |  | 2 | 2 | 2 | Unstarted | 0
|  |  | Planned Total | 178 | 92 | Actual Total | 25 | 25

## Page 2
SWE 3613 Status Report
Date |  | 2012-11-13
Members |  | Robin Mays, Thomas Couture, Matthew Powell, Lee Hall
Project |  | Forager - Group 4
Name |  | HOURS BY DEVELOPMENT ACTIVITY
|  | Requirements |  |  | Design / Prototype |  |  | Development / Code |  |  | Integrate / Test |  |  | Documentation |  |  | Totals
|  | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total
Robin Mays |  | 1 | 0 |  | 4 | 1 | 1 | 14 | 4 | 4 | 5 | 0 |  | 4 | 0.5 | 0.5 | 28 | 5.5 | 5.5
Thomas Couture |  | 1 | 0 |  | 4 | 2 | 2 | 14 | 5 | 5 | 5 | 0 |  | 4 | 1 | 1 | 28 | 8 | 8
Matthew Powell |  | 1 | 0 |  | 4 | 3 | 3 | 14 | 2 | 2 | 5 | 0 |  | 4 | 0 |  | 28 | 5 | 5
Lee Hall |  | 1 | 0 |  | 4 | 1 | 1 | 14 | 5 | 5 | 5 | 2 | 2 | 4 | 0 |  | 28 | 8 | 8
| Totals: | 4 | 0 | 0 | 16 | 7 | 7 | 56 | 16 | 16 | 20 | 2 | 2 | 16 | 1.5 | 1.5 | 112 |  | 26.5
Name |  | HOURS BY USER STORY
|  | Crawler 1 |  | Crawler 2 |  | Report 1 |  | Report 2 |  | Report 3 |  | Report 4 |  | Report 5 |  | Report 6 |  | Crawler 3
|  | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle
Robin Mays | [5 empty] | 1 | 1 |  |  | 4 | 4
Thomas Couture | [5 empty] | 2 | 2 |  |  | 4 | 4
Matthew Powell
Lee Hall |  | 7 | 7 | [10 empty] | 1 | 1
| Totals: | 7 | 7 | 0 | 0 | 3 | 3 | 0 | 0 | 8 | 8 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
|  | Crawler 4 |  | SSL |  | Report 7 |  | Login |  | Crawler 5 |  | Crawler 6 |  | Crawler 7 |  | 0 |  | Totals
|  | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle
Robin Mays | [17 empty] | 5 | 5
Thomas Couture | [7 empty] | 1 | 1 | [8 empty] | 7 | 7
Matthew Powell |  | 5 | 5 | [14 empty] | 5 | 5
Lee Hall | [17 empty] | 8 | 8
| Totals: | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25
Accomplishments since last status report:
Login UI has been completed. Starting a scan UI has made progress. Web Crawler was reworked to pick up extra links that were missing. Table was updated to include a next page feature and to not include the 200 responses.
Obstacles encountered since last status report:
Risks facing the project:
We could have library problems dealing with SSL pages. This can be mitigated by research, and is not a huge issue as it's a relatively low priority story. We could have communications problems between the report viewer and the web crawler.This would be a huge issue. A backup plan might be to use python to generate JSON directly from pickled object from the webcrawler, or potentially generate oneshot reports directly in the webcrawler, those these options are both less flexible.
Objectives for the next week:
Continue work on the UC's. Finish up all work on the webcrawler and get the table styled and completed. Make sure all sorting features are working. Start making progress on live reports and multiple report veiwing.
Notes:
Still waiting on the Scrum Master/Product Owner/Professor to look at the sprint backlog and give us feedback from cycle 1.

## Member 1 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Robin Mays
Week Ending: |  | 2012-11-13
Team Member Work Summary
Day: | Monday | Task(s) performed: | UI Banner Update
Date: | 2012-11-12 | Result: | Completed jpeg for websie update
Hours Worked: | 1 | Problems encountered:
Day: | Tuesday | Task(s) performed: | UI Updates/Login UI
Date: | 2012-11-13 | Result: | Completed Login UI and minor updates to UI
Hours Worked: | 3 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Meeting Minutes for Sprint Planning
Date: | 2012-11-07 | Result: | Took notes and wrote up Meeting minutes
Hours Worked: | 1 | Problems encountered:
Day: | Thursday | Task(s) performed: | Design/Documentation
Date: | 2012-11-08 | Result: | Met and discussed further project goals
Hours Worked: | 0.5 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2012-11-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2012-11-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2012-11-11 | Result:
Hours Worked: |  | Problems encountered:

## Member 2 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Thomas Couture
Week Ending: |  | 2012-11-13
Team Member Work Summary
Day: | Monday | Task(s) performed: | Start UI
Date: | 2012-11-12 | Result: | Basic UI for Start
Hours Worked: | 1 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Login UI, Banner Update, Weekly Status Report
Date: | 2012-11-13 | Result: | Login UI Complete, Banner updates, Table Updates
Hours Worked: | 6.5 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2012-11-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Design/Documentation
Date: | 2012-11-08 | Result: | Met and discussed further project goals
Hours Worked: | 0.5 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2012-11-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2012-11-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2012-11-11 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 3 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Matthew Powell
Week Ending: |  | 2012-11-13
Team Member Work Summary
Day: | Monday | Task(s) performed: | UC Crawler 4 Design and Code
Date: | 2012-11-12 | Result: | Designed and code in process
Hours Worked: | 4 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Design/Documentation
Date: | 2012-11-13 | Result: | Met and discussed further project goals
Hours Worked: | 0.5 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2012-11-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Design/Documentation
Date: | 2012-11-08 | Result: | Met and discussed further project goals
Hours Worked: | 0.5 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2012-11-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2012-11-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2012-11-11 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 4 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Lee Hall
Week Ending: |  | 2012-11-13
Team Member Work Summary
Day: | Monday | Task(s) performed: | Testing, Coding
Date: | 2012-11-12 | Result: | Debugged crawler-1 to retrive more results
Hours Worked: | 5 | Problems encountered: | Inlined images on pages and invalid html
Day: | Tuesday | Task(s) performed: | Design/Documentation
Date: | 2012-11-13 | Result: | Met and discussed further project goals
Hours Worked: | 0.5 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2012-11-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Design/Documentation
Date: | 2012-11-08 | Result: | Met and discussed further project goals
Hours Worked: | 0.5 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2012-11-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Testing, Coding
Date: | 2012-11-10 | Result: | Debugged crawler-1 to retrive more results
Hours Worked: | 2 | Problems encountered: | There are URI schemes that we cannot check (mms://)
Day: | Sunday | Task(s) performed:
Date: | 2012-11-11 | Result:
Hours Worked: | 0 | Problems encountered:

## Computation (hidden)
Week: | 1 |  | Total Weeks: | 3
|  |  | Total Days | 21
Member | 2012-11-09 | 2012-11-10 | 2012-11-11 | 2012-11-12 | 2012-11-13 | 2012-11-07 | 2012-11-08 | Week Total | Page2 == Timesheet | Hours not in a user story
Robin Mays | 0 | 0 | 0 | 1 | 3 | 1 | 0.5 | 5.5 | PASS | 0.5
Thomas Couture | 0 | 0 | 0 | 1 | 6.5 | 0 | 0.5 | 8 | PASS | 1
Matthew Powell | 0 | 0 | 0 | 4 | 0.5 | 0 | 0.5 | 5 | PASS | 0
Lee Hall | 0 | 2 | 0 | 5 | 0.5 | 0 | 0.5 | 8 | PASS | 0
Total | 0 | 2 | 0 | 11 | 10.5 | 1 | 2 | 26.5 | FAIL | -25
Member | 2012-11-07 | 2012-11-08 | 2012-11-09 | 2012-11-10 | 2012-11-11 | 2012-11-12 | 2012-11-13 |  | Page1==Page2 Stories | Percent of hours in user stories
Robin Mays | 1 | 0.5 | 0 | 0 | 0 | 1 | 3 |  | PASS | 0.90909
Thomas Couture | 0 | 0.5 | 0 | 0 | 0 | 1 | 6.5 |  |  | 0.875
Matthew Powell | 0 | 0.5 | 0 | 0 | 0 | 4 | 0.5 |  |  | 1
Lee Hall | 0 | 0.5 | 0 | 2 | 0 | 5 | 0.5 |  |  | 1
Total | 1 | 2 | 0 | 2 | 0 | 11 | 10.5
| 0 | 1 | 2 | 3 | 4 | 5 | 6
| 2012-11-07 | 2012-11-08 | 2012-11-09 | 2012-11-10 | 2012-11-11 | 2012-11-12 | 2012-11-13
Robin Mays | 27.0909 | 26.6364 | 26.6364 | 26.6364 | 26.6364 | 25.7273 | 23
Thomas Couture | 28 | 27.5625 | 27.5625 | 27.5625 | 27.5625 | 26.6875 | 21
Matthew Powell | 28 | 27.5 | 27.5 | 27.5 | 27.5 | 23.5 | 23
Lee Hall | 28 | 27.5 | 27.5 | 25.5 | 25.5 | 20.5 | 20
Ideal | 112 | 106.6667 | 101.3333 | 96 | 90.6667 | 85.3333 | 80
Actual | 111.0909 | 109.1989 | 109.1989 | 107.1989 | 107.1989 | 96.4148 | 87