## Status Report Template
SWE 3613 Status Report
IMPORTANT: File naming instructions
Name this file in the following manner: YYYYMMDD_TEAM_NAME_HERE.pdf
Example: 20120911_Group1.pdf
List Data - Do Not Edit
Project Name |  | Forager - Group 4 | [6 empty] | Completed | 1
Team Members |  | Robin Mays, Thomas Couture, Matthew Powell, Lee Hall | [6 empty] | Discarded | 2
Week Ending: |  | 2012-11-06 | [6 empty] | Development | 3
Cycle |  | Cycle 1 | [6 empty] | Testing | 4
System Metaphor |  | The system is designed to check through the entire SPSU domain and return a detailed report. This report should include all errors including dead links, missing images, scripts, and css files. All reports created should be stored and accessable through an easy to use user interface. These reports should also be sortable to make it easier to find certain reports, as well as comparable to each other to check and see the differences between them. It was also include features such as pausing, stoping, or restricting a search. | [6 empty] | Design | 5
Cycle Intent |  | The intent of this cycle is to get the web crawler working. That includes getting the web crawler to not just search through the different pages, but to also return the errors that it encounters. We also plan on taking those results and putting them into a user friendly report to be examined through our user interface. We plan on having the web crawler functional through our user interface. We also plan on completing the login for security purposes. | [6 empty] | Unstarted | 6
ID | Use Case Name |  | Planned |  |  | Actual
|  |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
Crawler 1 | Basic Web Crawler |  | 1 | 20 | 20 | Completed | 0 | 8
Crawler 2 | Record Crawler Results |  | 1 | 20 | 20 | Completed | 10 | 15
Report 1 | Show Scan Results |  | 1 | 30 | 30 | Completed | 16.5 | 29.5
Report 2 | Crawler Interaction |  | 1 | 20 | 20 | Completed | 9 | 9
Report 3 | Sort Report |  | 2 | 10 | 0 | Unstarted | 0
Report 4 | Print Report |  | 2 | 10 | 0 | Unstarted | 0
Report 5 | Multiple Report Changes |  | 2 | 6 | 0 | Unstarted | 0
Report 6 | Live Report |  | 2 | 4 | 0 | Unstarted | 0
Crawler 3 | Runtime Limit |  | 2 | 12 | 0 | Unstarted | 0
Crawler 4 | Error Check |  | 2 | 10 | 0 | Unstarted | 0
SSL | Secure Check |  | 2 | 8 | 0 | Unstarted | 0
Report 7 | Subdomain Sort |  | 2 | 14 | 0 | Unstarted | 0
Login | User Login |  | 1 | 2 | 2 | Development | 0 | 1
Crawler 5 | Pause Scan |  | 2 | 4 | 0 | Unstarted | 0
Crawler 6 | Timer |  | 2 | 6 | 0 | Unstarted | 0
Crawler 7 | Stopwatch |  | 2 | 2 | 0 | Unstarted | 0
|  |  | Planned Total | 178 | 92 | Actual Total | 35.5 | 62.5

## Page 2
SWE 3613 Status Report
Date |  | 2012-11-06
Members |  | Robin Mays, Thomas Couture, Matthew Powell, Lee Hall
Project |  | Forager - Group 4
Name |  | HOURS BY DEVELOPMENT ACTIVITY
|  | Requirements |  |  | Design / Prototype |  |  | Development / Code |  |  | Integrate / Test |  |  | Documentation |  |  | Totals
|  | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total
Robin Mays |  | 4 | 0 | 5 | 5 | 0 | 2 | 17 | 7 | 9 | 3 | 1 | 1 | 4 | 4 | 4.5 | 33 | 12 | 21.5
Thomas Couture |  | 4 | 0 | 4 | 5 | 0 | 4 | 17 | 9.5 | 12.5 | 3 | 1 | 1 | 4 | 2 | 5 | 33 | 12.5 | 26.5
Matthew Powell |  | 4 | 0 | 5 | 4 | 0 | 4 | 13 | 5 | 5 | 3 | 2 | 2 | 4 | 6 | 6.5 | 28 | 13 | 22.5
Lee Hall |  | 4 | 0 | 5 | 2 | 0 | 2 | 13 | 8 | 16 | 5 | 2 | 4 | 4 | 0 | 4 | 28 | 10 | 31
| Totals: | 16 | 0 | 19 | 16 | 0 | 12 | 60 | 29.5 | 42.5 | 14 | 6 | 8 | 16 | 12 | 20 | 122 | 47.5 | 101.5
Name |  | HOURS BY USER STORY
|  | Crawler 1 |  | Crawler 2 |  | Report 1 |  | Report 2 |  | Report 3 |  | Report 4 |  | Report 5 |  | Report 6 |  | Crawler 3
|  | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle
Robin Mays | [5 empty] | 7 | 11 | 1 | 1
Thomas Couture | [5 empty] | 8.5 | 16.5 | 2 | 2
Matthew Powell |  |  |  | 5 | 9 | 1 | 1 | 1 | 1
Lee Hall |  |  | 8 | 5 | 6 |  | 1 | 5 | 5
| Totals: | 0 | 8 | 10 | 15 | 16.5 | 29.5 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Crawler 4 |  | SSL |  | Report 7 |  | Login |  | Crawler 5 |  | Crawler 6 |  | Crawler 7 |  | 0 |  | Totals
|  | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle
Robin Mays | [17 empty] | 8 | 12
Thomas Couture | [17 empty] | 10.5 | 18.5
Matthew Powell | [17 empty] | 7 | 11
Lee Hall | [8 empty] | 1 | [8 empty] | 10 | 21
| Totals: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.5 | 62.5
Accomplishments since last status report:
Updates to the UI. Robin and Thomas completed Use Case Report 1. Matthew and Lee completed Use Case Crawler 2. Lee finished up Use Case Report 2.
Obstacles encountered since last status report:
Risks facing the project:
We could have library problems dealing with SSL pages. This can be mitigated by research, and is not a huge issue as it's a relatively low priority story. We could have communications problems between the report viewer and the web crawler.This would be a huge issue. A backup plan might be to use python to generate JSON directly from pickled object from the webcrawler, or potentially generate oneshot reports directly in the webcrawler, those these options are both less flexible.
Objectives for the next week:
Spring Planning meeting and starting to make progress on Sprint 2.
Notes:

## Member 1 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Robin Mays
Week Ending: |  | 2012-11-06
Team Member Work Summary
Day: | Monday | Task(s) performed: | Documentation
Date: | 2012-11-05 | Result: | Sprint 1 report/Power Point
Hours Worked: | 2 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2012-11-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2012-10-31 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | UI Coding
Date: | 2012-11-01 | Result: | Work completed on Reports/ Scans
Hours Worked: | 3 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2012-11-02 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Coding for Report 1
Date: | 2012-11-03 | Result: | Results are displayed on Website
Hours Worked: | 5 | Problems encountered:
Day: | Sunday | Task(s) performed: | Documentation
Date: | 2012-11-04 | Result: | Sprint 1 report
Hours Worked: | 2 | Problems encountered:

## Member 2 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Thomas Couture
Week Ending: |  | 2012-11-06
Team Member Work Summary
Day: | Monday | Task(s) performed: | UI updates/fixes and Final Doc
Date: | 2012-11-05 | Result: | UI touchup work
Hours Worked: | 3 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Final Report/Power Point
Date: | 2012-11-06 | Result: | Last touch up work and submission
Hours Worked: | 1 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2012-10-31 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | UI Coding
Date: | 2012-11-01 | Result: | Work completed on Report and Scans page
Hours Worked: | 2 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2012-11-02 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Coding for Report 1
Date: | 2012-11-03 | Result: | Results are displayed on Website
Hours Worked: | 5 | Problems encountered:
Day: | Sunday | Task(s) performed: | Status Report
Date: | 2012-11-04 | Result: | Final status report and final changes
Hours Worked: | 1.5 | Problems encountered:

## Member 3 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Matthew Powell
Week Ending: |  | 2012-11-06
Team Member Work Summary
Day: | Monday | Task(s) performed: | Sprint Report
Date: | 2012-11-05 | Result: | Post Mortem Analysis
Hours Worked: | 1 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Documentation
Date: | 2012-11-06 | Result: | Post Mortem, Test Plan, Screenshots, Power Point
Hours Worked: | 5 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2012-10-31 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2012-11-01 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2012-11-02 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Coding on Crawler 2
Date: | 2012-11-03 | Result: | Completed Crawler 2 Use Case
Hours Worked: | 5 | Problems encountered:
Day: | Sunday | Task(s) performed: | Test Plan
Date: | 2012-11-04 | Result: | Testing Use Case Crawler 2, Report 1, Report 2
Hours Worked: | 2 | Problems encountered:

## Member 4 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Lee Hall
Week Ending: |  | 2012-11-06
Team Member Work Summary
Day: | Monday | Task(s) performed: | Testing of Report 2
Date: | 2012-11-05 | Result: | Worked on Signal Handling between Crawler and Web
Hours Worked: | 2 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2012-11-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2012-10-31 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2012-11-01 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2012-11-02 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Coding Crawler 2
Date: | 2012-11-03 | Result: | Completed Crawler 2 use case
Hours Worked: | 5 | Problems encountered:
Day: | Sunday | Task(s) performed: | Worked on Report 2
Date: | 2012-11-04 | Result: | Integration of Web Crawler with Web UI
Hours Worked: | 3 | Problems encountered:

## Computation (hidden)
Week: | 1 |  | Total Weeks: | 3
|  |  | Total Days | 21
Member | 2012-11-02 | 2012-11-03 | 2012-11-04 | 2012-11-05 | 2012-11-06 | 2012-10-31 | 2012-11-01 | Week Total | Page2 == Timesheet | Hours not in a user story
Robin Mays | 0 | 5 | 2 | 2 | 0 | 0 | 3 | 12 | PASS | 4
Thomas Couture | 0 | 5 | 1.5 | 3 | 1 | 0 | 2 | 12.5 | PASS | 2
Matthew Powell | 0 | 5 | 2 | 1 | 5 | 0 | 0 | 13 | PASS | 6
Lee Hall | 0 | 5 | 3 | 2 | 0 | 0 | 0 | 10 | PASS | 0
Total | 0 | 20 | 8.5 | 8 | 6 | 0 | 5 | 47.5 | PASS | 12
Member | 2012-10-31 | 2012-11-01 | 2012-11-02 | 2012-11-03 | 2012-11-04 | 2012-11-05 | 2012-11-06 |  | Page1==Page2 Stories | Percent of hours in user stories
Robin Mays | 0 | 3 | 0 | 5 | 2 | 2 | 0 |  | PASS | 0.66667
Thomas Couture | 0 | 2 | 0 | 5 | 1.5 | 3 | 1 |  |  | 0.84
Matthew Powell | 0 | 0 | 0 | 5 | 2 | 1 | 5 |  |  | 0.53846
Lee Hall | 0 | 0 | 0 | 5 | 3 | 2 | 0 |  |  | 1
Total | 0 | 5 | 0 | 20 | 8.5 | 8 | 6
| 0 | 1 | 2 | 3 | 4 | 5 | 6
| 2012-10-31 | 2012-11-01 | 2012-11-02 | 2012-11-03 | 2012-11-04 | 2012-11-05 | 2012-11-06
Robin Mays | 33 | 31 | 31 | 27.6667 | 26.3333 | 25 | 25
Thomas Couture | 33 | 31.32 | 31.32 | 27.12 | 25.86 | 23.34 | 22.5
Matthew Powell | 28 | 28 | 28 | 25.3077 | 24.2308 | 23.6923 | 21
Lee Hall | 28 | 28 | 28 | 23 | 20 | 18 | 18
Ideal | 122 | 116.1905 | 110.381 | 104.5714 | 98.7619 | 92.9524 | 87.1429
Actual | 122 | 118.32 | 118.32 | 103.0944 | 96.4241 | 90.0323 | 86.5