## Status Report Template
SWE 3613 Status Report
IMPORTANT: File naming instructions
Name this file in the following manner: YYYYMMDD_TEAM_NAME_HERE.pdf
Example: 20120911_Group1.pdf
List Data - Do Not Edit
Project Name |  | Forager - Group 4 | [6 empty] | Completed | 1
Team Members |  | Robin Mays, Thomas Couture, Matthew Powell, Lee Hall | [6 empty] | Discarded | 2
Week Ending: |  | 2012-10-23 | [6 empty] | Development | 3
Cycle |  | Cycle 1 | [6 empty] | Testing | 4
System Metaphor |  | The system is designed to check through the entire SPSU domain and return a detailed report. This report should include all errors including dead links, missing images, scripts, and css files. All reports created should be stored and accessable through an easy to use user interface. These reports should also be sortable to make it easier to find certain reports, as well as comparable to each other to check and see the differences between them. It was also include features such as pausing, stoping, or restricting a search. | [6 empty] | Design | 5
Cycle Intent |  | The intent of this cycle is to get the web crawler working. That includes getting the web crawler to not just search through the different pages, but to also return the errors that it encounters. We also plan on taking those results and putting them into a user friendly report to be examined through our user interface. We plan on having the web crawler functional through our user interface. We also plan on completing the login for security purposes. | [6 empty] | Unstarted | 6
# | User Story |  | Planned |  |  | Actual
|  |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | As a user, I would like to be able to visit and access all pages of my website. |  | 1 | 20 | 20 | Unstarted | 0
2 | As a user, I would like this program to record any resources that are unavailable, including dead links, missing images, scripts or css files. |  | 1 | 20 | 20 | Design | 3 | 3
3 | As a user I must be able to view a report of a given scan. This report should show all broken links and missing images that fall under my domain. These scans should be listed and accessible from a website. |  | 1 | 30 | 30 | Design | 3 | 3
4 | As a user, I would like to view scans and start new scans from a website. |  | 1 | 20 | 20 | Unstarted | 0
5 | As a user viewing a report, I should be able to generate that report in a printer friendly format. |  | 2 | 10 | 0 | Unstarted | 0
6 | As a user viewing a report, I should be able to generate that report in a printer friendly format. |  | 2 | 10 | 0 | Unstarted | 0
7 | As a user, I would like to be able to select two scans and show only the items that have changed. |  | 2 | 6 | 0 | Unstarted | 0
8 | As a user viewing a report, I should be able to view reports from scans that are in progress. |  | 2 | 4 | 0 | Unstarted | 0
9 | As a user, I would like to be able to limit the run time of a scan when I start it, either by time, or by distance from the start page. |  | 2 | 12 | 0 | Unstarted | 0
10 | As a user I would like to select a scan, and run a new scan that will check if the previous errors have been corrected. |  | 2 | 10 | 0 | Unstarted | 0
11 | As a user, I would like for reports to include pages that are accessible over secured links. |  | 2 | 8 | 0 | Unstarted | 0
12 | As a user, I would like to sort a report based on the subdomain. |  | 2 | 14 | 0 | Unstarted | 0
13 | As a user, I should have to login before initiating a scan or viewing a report. |  | 1 | 2 | 2 | Completed | 1 | 1
14 | As a user, I might like to pause a scan that was currently in progress. |  | 2 | 4 | 0 | Unstarted | 0
15 | As a user, having Scans that were automatically run at regular intervals. |  | 2 | 6 | 0 | Unstarted | 0
16 | As a user I would like to see page load times in my reports. |  | 2 | 2 | 0 | Unstarted | 0
|  |  | Planned Total | 178 | 92 | Actual Total | 7 | 7

## Page 2
SWE 3613 Status Report
Date |  | 2012-10-23
Members |  | Robin Mays, Thomas Couture, Matthew Powell, Lee Hall
Project |  | Forager - Group 4
Name |  | HOURS BY DEVELOPMENT ACTIVITY
|  | Requirements |  |  | Design / Prototype |  |  | Development / Code |  |  | Integrate / Test |  |  | Documentation |  |  | Totals
|  | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total
Robin Mays |  |  | 3 | 3 |  |  |  | 25 | [6 empty] | 0.5 | 0.5 | 25 | 3.5 | 3.5
Thomas Couture |  |  | 2 | 2 |  | 2 | 2 | 25 | [6 empty] | 2 | 2 | 25 | 6 | 6
Matthew Powell |  |  | 3 | 3 |  | 2 | 2 | 20 | [6 empty] | 0.5 | 0.5 | 20 | 5.5 | 5.5
Lee Hall |  |  | 3 | 3 |  | 2 | 2 | 20 | [6 empty] | 3 | 3 | 20 | 8 | 8
| Totals: | 0 | 11 | 11 | 0 | 6 | 6 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 90 | 23 | 23
Name |  | HOURS BY USER STORY
|  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
|  | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle
Robin Mays
Thomas Couture | [5 empty] | 2 | 2
Matthew Powell |  |  |  | 2 | 2
Lee Hall |  |  |  | 1 | 1 | 1 | 1
| Totals: | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 0 |  | Totals
|  | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle
Robin Mays | [17 empty] | 0 | 0
Thomas Couture | [17 empty] | 2 | 2
Matthew Powell | [17 empty] | 2 | 2
Lee Hall | [7 empty] | 1 | 1 | [8 empty] | 3 | 3
| Totals: | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7
Accomplishments since last status report:
Completed the User Stories. Divided up the work load for the project. Database and backend set up. Github up and ready.
Obstacles encountered since last status report:
Risks facing the project:
We could have library problems dealing with SSL pages. This can be mitigated by research, and is not a huge issue as it's a relatively low priority story. We could have communications problems between the report viewer and the web crawler.This would be a huge issue. A backup plan might be to use python to generate JSON directly from pickled object from the webcrawler, or potentially generate oneshot reports directly in the webcrawler, those these options are both less flexible.
Objectives for the next week:
Have the webcrawler complete and ready to be integrated into the UI. Have the UI complete and ready for the integration. Login page completed. Begin work on report viewing.
Notes:
Database and Github was reused from last project. Work to shift over from last project to this was minimal (10 minutes) and thus not added in to the work.

## Member 1 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Robin Mays
Week Ending: |  | 2012-10-23
Team Member Work Summary
Day: | Monday | Task(s) performed:
Date: | 2012-10-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Status Report
Date: | 2012-10-23 | Result: | Completed personal section of Report/proof read.
Hours Worked: | 0.5 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Worked on User Stories
Date: | 2012-10-17 | Result: | Work towards completion of first draft.
Hours Worked: | 2 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2012-10-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Final User Stories
Date: | 2012-10-19 | Result: | Work towards completion of first draft.
Hours Worked: | 1 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2012-10-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2012-10-21 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 2 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Thomas Couture
Week Ending: |  | 2012-10-23
Team Member Work Summary
Day: | Monday | Task(s) performed:
Date: | 2012-10-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Weekly Status Report
Date: | 2012-10-23 | Result: | Completed Weekly Status report
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Worked on User Stories
Date: | 2012-10-17 | Result: | Work towards completion of first draft.
Hours Worked: | 1 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2012-10-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Final Copy of User Stories
Date: | 2012-10-19 | Result: | Work towards completion of first draft.
Hours Worked: | 1 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2012-10-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Swaign work for UI
Date: | 2012-10-21 | Result: | Made progress on design of user story 3 and overall UI
Hours Worked: | 2 | Problems encountered: | slight language learning curve

## Member 3 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Matthew Powell
Week Ending: |  | 2012-10-23
Team Member Work Summary
Day: | Monday | Task(s) performed: | Design for User Story 2
Date: | 2012-10-22 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Weekly Status Report
Date: | 2012-10-23 | Result: | Completed personal section of report/proof read.
Hours Worked: | 0.5 | Problems encountered:
Day: | Wednesday | Task(s) performed: | First Draft of User Stories
Date: | 2012-10-17 | Result: | Completed first draft
Hours Worked: | 2 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2012-10-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Final draft of user stories
Date: | 2012-10-19 | Result: | work towards the completion of the final draft.
Hours Worked: | 1 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2012-10-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2012-10-21 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 4 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Lee Hall
Week Ending: |  | 2012-10-23
Team Member Work Summary
Day: | Monday | Task(s) performed:
Date: | 2012-10-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Documentation, Coding
Date: | 2012-10-23 | Result: | Setup documentation for burndown charts, Created login
Hours Worked: | 3 | Problems encountered: | Excel is occasionally ornery about pasting formulas
Day: | Wednesday | Task(s) performed: | Worked on user stories
Date: | 2012-10-17 | Result: | Worked towards completion of first draft.
Hours Worked: | 2 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2012-10-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Final User Stories
Date: | 2012-10-19 | Result: | Worked towards completion of first draft.
Hours Worked: | 1 | Problems encountered:
Day: | Saturday | Task(s) performed: | Design
Date: | 2012-10-20 | Result: | Built database schema
Hours Worked: | 2 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2012-10-21 | Result:
Hours Worked: | 0 | Problems encountered:

## Computation (hidden)
Week: | 1 |  | Total Weeks: | 3
|  |  | Total Days | 21
Member | 2012-10-19 | 2012-10-20 | 2012-10-21 | 2012-10-22 | 2012-10-23 | 2012-10-17 | 2012-10-18 | Week Total | Page2 == Timesheet | Hours not in a user story
Robin Mays | 1 | 0 | 0 | 0 | 0.5 | 2 | 0 | 3.5 | PASS | 3.5
Thomas Couture | 1 | 0 | 2 | 0 | 2 | 1 | 0 | 6 | PASS | 4
Matthew Powell | 1 | 0 | 0 | 2 | 0.5 | 2 | 0 | 5.5 | PASS | 3.5
Lee Hall | 1 | 2 | 0 | 0 | 3 | 2 | 0 | 8 | PASS | 5
Total | 4 | 2 | 2 | 2 | 6 | 7 | 0 | 23 | PASS | 16
Member | 2012-10-17 | 2012-10-18 | 2012-10-19 | 2012-10-20 | 2012-10-21 | 2012-10-22 | 2012-10-23 |  | Page1==Page2 Stories | Percent of hours in user stories
Robin Mays | 2 | 0 | 1 | 0 | 0 | 0 | 0.5 |  | PASS | 0
Thomas Couture | 1 | 0 | 1 | 0 | 2 | 0 | 2 |  |  | 0.33333
Matthew Powell | 2 | 0 | 1 | 0 | 0 | 2 | 0.5 |  |  | 0.36364
Lee Hall | 2 | 0 | 1 | 2 | 0 | 0 | 3 |  |  | 0.375
Total | 7 | 0 | 4 | 2 | 2 | 2 | 6
| 0 | 1 | 2 | 3 | 4 | 5 | 6
| 2012-10-17 | 2012-10-18 | 2012-10-19 | 2012-10-20 | 2012-10-21 | 2012-10-22 | 2012-10-23
Robin Mays | 25 | 25 | 25 | 25 | 25 | 25 | 25
Thomas Couture | 24.6667 | 24.6667 | 24.3333 | 24.3333 | 23.6667 | 23.6667 | 23
Matthew Powell | 19.2727 | 19.2727 | 18.9091 | 18.9091 | 18.9091 | 18.1818 | 18
Lee Hall | 19.25 | 19.25 | 18.875 | 18.125 | 18.125 | 18.125 | 17
Ideal | 90 | 85.7143 | 81.4286 | 77.1429 | 72.8571 | 68.5714 | 64.2857
Actual | 88.1894 | 88.1894 | 87.1174 | 86.3674 | 85.7008 | 84.9735 | 83