## Status Report Template
SWE 3613 Status Report
IMPORTANT: File naming instructions
Name this file in the following manner: YYYYMMDD_TEAM_NAME_HERE.pdf
Example: 20120911_Group1.pdf
List Data - Do Not Edit
Project Name |  | Forager - Group 4 | [6 empty] | Completed | 1
Team Members |  | Robin Mays, Thomas Couture, Matthew Powell, Lee Hall | [6 empty] | Discarded | 2
Week Ending: |  | 2012-11-27 | [6 empty] | Development | 3
Cycle |  | Cycle 1 | [6 empty] | Testing | 4
System Metaphor |  | The system is designed to check through the entire SPSU domain and return a detailed report. This report should include all errors including dead links, missing images, scripts, and css files. All reports created should be stored and accessable through an easy to use user interface. These reports should also be sortable to make it easier to find certain reports, as well as comparable to each other to check and see the differences between them. It was also include features such as pausing, stoping, or restricting a search. | [6 empty] | Design | 5
Cycle Intent |  | The intent of this cycle is to get the added features of the product working. We plan to include sorting, printing, and comparing of the reports. We plan to be able to start a new scan of something previously scanned. Features to limit the scan based on certain criteria. Ability to pause and stop the scan. | [6 empty] | Unstarted | 6
ID | Use Case Name |  | Planned |  |  | Actual
|  |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
Crawler 1 | Basic Web Crawler |  | 2 | 20 | 5 | Completed | 7 | 15
Crawler 2 | Record Crawler Results |  | 1 | 20 | 0 | Completed | 0 | 15
Report 1 | Show Scan Results |  | 2 | 30 | 4 | Testing | 4 | 33.5
Report 2 | Crawler Interaction |  | 1 | 20 |  | Completed | 0 | 9
Report 3 | Sort Report |  | 2 | 10 | 10 | Completed | 10 | 10
Report 4 | Print Report |  | 2 | 10 | 10 | Development | 7 | 7
Report 5 | Multiple Report Changes |  | 2 | 6 | 6 | Testing | 8 | 8
Report 6 | Live Report |  | 2 | 4 | 4 | Development | 7 | 7
Crawler 3 | Runtime Limit |  | 2 | 12 | 12 | Testing | 9.5 | 9.5
Crawler 4 | Error Check |  | 2 | 10 | 10 | Testing | 10.5 | 10.5
SSL | Secure Check |  | 2 | 8 | 8 | Testing | 0.5 | 0.5
Report 7 | Subdomain Sort |  | 2 | 14 | 14 | Development | 9.5 | 9.5
Login | User Login |  | 2 | 2 | 1 | Completed | 1.5 | 2.5
Crawler 5 | Pause Scan |  | 2 | 4 | 4 | Testing | 11.5 | 11.5
Crawler 6 | Timer |  | 2 | 6 | 2 | Testing | 1 | 1
Crawler 7 | Stopwatch |  | 2 | 2 | 2 | Testing | 1 | 1
|  |  | Planned Total | 178 | 92 | Actual Total | 88 | 150.5

## Page 2
SWE 3613 Status Report
Date |  | 2012-11-27
Members |  | Robin Mays, Thomas Couture, Matthew Powell, Lee Hall
Project |  | Forager - Group 4
Name |  | HOURS BY DEVELOPMENT ACTIVITY
|  | Requirements |  |  | Design / Prototype |  |  | Development / Code |  |  | Integrate / Test |  |  | Documentation |  |  | Totals
|  | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total | Cycle Plan | Week Actual | Cycle Total
Robin Mays |  | 1 | 0 | 0 | 4 | 1 | 2 | 14 | 9 | 14 | 5 | 2 | 2 | 4 | 2 | 1.5 | 28 | 14 | 19.5
Thomas Couture |  | 1 | 0 | 0 | 4 | 1 | 3 | 14 | 10 | 16 | 5 | 2 | 2 | 4 | 2 | 4 | 28 | 15 | 25
Matthew Powell |  | 1 | 0 | 0 | 4 | 1 | 3 | 14 | 11 | 13 | 5 | 1 | 5 | 4 | 2 | 2.5 | 28 | 15 | 23.5
Lee Hall |  | 1 | 0 | 0 | 4 | 2 | 3 | 14 | 12 | 19 | 5 | 4 | 6 | 4 | 0 | 2.5 | 28 | 18 | 30.5
| Totals: | 4 | 0 | 0 | 16 | 5 | 11 | 56 | 42 | 62 | 20 | 9 | 15 | 16 | 6 | 10.5 | 112 | 62 | 98.5
Name |  | HOURS BY USER STORY
|  | Crawler 1 |  | Crawler 2 |  | Report 1 |  | Report 2 |  | Report 3 |  | Report 4 |  | Report 5 |  | Report 6 |  | Crawler 3
|  | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle
Robin Mays | [5 empty] | 0 | 2 |  |  | 1 | 6 | 4 | 4 | 1 | 1
Thomas Couture | [5 empty] | 0 | 2 |  |  | 0 | 4 | 3 | 3 | 4 | 6
Matthew Powell | [17 empty] | 7 | 7.5
Lee Hall |  | 0 | 7 | [10 empty] | 0 | 1 | 7 | 7 | 2 | 2
| Totals: | 0 | 7 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 10 | 7 | 7 | 5 | 8 | 7 | 7 | 9 | 9.5
|  | Crawler 4 |  | SSL |  | Report 7 |  | Login |  | Crawler 5 |  | Crawler 6 |  | Crawler 7 |  | 0 |  | Totals
|  | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle | This Week | This Cycle
Robin Mays | [5 empty] | 4 | 4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 11 | 18
Thomas Couture | [5 empty] | 5 | 5 | 0 | 1 | [8 empty] | 12 | 21
Matthew Powell |  | 5 | 10.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 |  |  | 12 | 21
Lee Hall | [9 empty] | 9 | 11 | [6 empty] | 18 | 28
| Totals: | 5 | 10.5 | 0 | 0.5 | 9 | 9.5 | 0 | 1.5 | 9 | 11.5 | 0.5 | 1 | 0.5 | 1 | 0 | 0 | 53 | 88
Accomplishments since last status report:
Almost all functionality is in the testing phase. Scans can be run from the web UI as well as paused, resumed and stopped. You can compare multiple reports, start scans based on old reports, limit the runtime of new scans.
Obstacles encountered since last status report:
Printing problem in conjunction with the way we are displaying our table. Slow load time on the live scan has lead us to trying alternatives to get a feasable live runtime scan.
Risks facing the project:
We could have library problems dealing with SSL pages. This can be mitigated by research, and is not a huge issue as it's a relatively low priority story. We could have communications problems between the report viewer and the web crawler.This would be a huge issue. A backup plan might be to use python to generate JSON directly from pickled object from the webcrawler, or potentially generate oneshot reports directly in the webcrawler, those these options are both less flexible.
Objectives for the next week:
Finish up any testing, and complete our Final Report and Power Point Presentation.
Notes:

## Member 1 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Robin Mays
Week Ending: |  | 2012-11-27
Team Member Work Summary
Day: | Monday | Task(s) performed: | Worked on completing UC Report 4,5,7
Date: | 2012-11-26 | Result: | Completed Reoprt 4 and 5, Progress towards 7
Hours Worked: | 6 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Final Report Doc/Meeting Minutes
Date: | 2012-11-27 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2012-11-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2012-11-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2012-11-23 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2012-11-24 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Worked on completing UC Report 3,4,5,7
Date: | 2012-11-25 | Result: | Completed Reoprt 3, Progress towards 4 and 5
Hours Worked: | 6 | Problems encountered:

## Member 2 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Thomas Couture
Week Ending: |  | 2012-11-27
Team Member Work Summary
Day: | Monday | Task(s) performed: | Worked on completing UC Report 4,5,7
Date: | 2012-11-26 | Result: | Completed Reoprt 4 and 5, Progress towards 7
Hours Worked: | 7 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Status report rework, new report, and burndowns
Date: | 2012-11-27 | Result: | Completed reports/charts
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2012-11-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2012-11-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2012-11-23 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2012-11-24 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Worked on completing UC Report 3,4,5,7
Date: | 2012-11-25 | Result: | Completed Reoprt 3, Progress towards 4 and 5
Hours Worked: | 6 | Problems encountered:

## Member 3 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Matthew Powell
Week Ending: |  | 2012-11-27
Team Member Work Summary
Day: | Monday | Task(s) performed: | Finished up UC Crawler 3
Date: | 2012-11-26 | Result: | Runtime finctionality works
Hours Worked: | 2 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Final Doc/Testing
Date: | 2012-11-27 | Result:
Hours Worked: | 3 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2012-11-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2012-11-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2012-11-23 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Worked on Crawler 4
Date: | 2012-11-24 | Result: | Completed Running scans on previous reports
Hours Worked: | 5 | Problems encountered:
Day: | Sunday | Task(s) performed: | Worked on Crawler 3
Date: | 2012-11-25 | Result: | Progress towards completing UC
Hours Worked: | 5 | Problems encountered:

## Member 4 Timesheet
SWE 3613 Timesheet
Project Name: |  | Forager - Group 4
Member: |  | Lee Hall
Week Ending: |  | 2012-11-27
Team Member Work Summary
Day: | Monday | Task(s) performed: | Testing
Date: | 2012-11-26 | Result: | Fixed Web UI for Scan Controls
Hours Worked: | 3 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Report 6
Date: | 2012-11-27 | Result: | Changed logs to splint into chunks serverside
Hours Worked: | 2 | Problems encountered: | The DataTables module does not deal with this particularly well. This will probably be reverted.
Day: | Wednesday | Task(s) performed: | Crawler 5
Date: | 2012-11-21 | Result: | Pause functionality working (crawler side only)
Hours Worked: | 3 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2012-11-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2012-11-23 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Worked on Crawler 4 and 5
Date: | 2012-11-24 | Result: | Php can send signals to pause and resume crawler
Hours Worked: | 5 | Problems encountered:
Day: | Sunday | Task(s) performed: | Worked on Report 6 and Testing
Date: | 2012-11-25 | Result: | Bugs fixed in interface
Hours Worked: | 5 | Problems encountered: | Getting a constant stream of data is difficult, as loading large JSON takes a long time.

## Computation (hidden)
Week: | 1 |  | Total Weeks: | 3
|  |  | Total Days | 21
Member | 2012-11-23 | 2012-11-24 | 2012-11-25 | 2012-11-26 | 2012-11-27 | 2012-11-21 | 2012-11-22 | Week Total | Page2 == Timesheet | Hours not in a user story
Robin Mays | 0 | 0 | 6 | 6 | 2 | 0 | 0 | 14 | PASS | 3
Thomas Couture | 0 | 0 | 6 | 7 | 2 | 0 | 0 | 15 | PASS | 3
Matthew Powell | 0 | 5 | 5 | 2 | 3 | 0 | 0 | 15 | PASS | 3
Lee Hall | 0 | 5 | 5 | 3 | 2 | 3 | 0 | 18 | PASS | 0
Total | 0 | 10 | 22 | 18 | 9 | 3 | 0 | 62 | PASS | 9
Member | 2012-11-21 | 2012-11-22 | 2012-11-23 | 2012-11-24 | 2012-11-25 | 2012-11-26 | 2012-11-27 |  | Page1==Page2 Stories | Percent of hours in user stories
Robin Mays | 0 | 0 | 0 | 0 | 6 | 6 | 2 |  | FAIL | 0.78571
Thomas Couture | 0 | 0 | 0 | 0 | 6 | 7 | 2 |  |  | 0.8
Matthew Powell | 0 | 0 | 0 | 5 | 5 | 2 | 3 |  |  | 0.8
Lee Hall | 3 | 0 | 0 | 5 | 5 | 3 | 2 |  |  | 1
Total | 3 | 0 | 0 | 10 | 22 | 18 | 9
| 0 | 1 | 2 | 3 | 4 | 5 | 6
| 2012-11-21 | 2012-11-22 | 2012-11-23 | 2012-11-24 | 2012-11-25 | 2012-11-26 | 2012-11-27
Robin Mays | 28 | 28 | 28 | 28 | 23.2857 | 18.5714 | 17
Thomas Couture | 28 | 28 | 28 | 28 | 23.2 | 17.6 | 16
Matthew Powell | 28 | 28 | 28 | 24 | 20 | 18.4 | 16
Lee Hall | 25 | 25 | 25 | 20 | 15 | 12 | 10
Ideal | 112 | 106.6667 | 101.3333 | 96 | 90.6667 | 85.3333 | 80
Actual | 109 | 109 | 109 | 100 | 81.4857 | 66.5714 | 59